## Overall_Project_Schedule
T3 Project Schedule
Submission Deadline |  |  | 11 p.m. @ 2/13/18
Date | Deliverable | Subtasks | Status | Notes
2018-02-07 | User stories |  | In-process
| Wireframes |  | In-process
2018-02-09 | Game engine |  | Pending
2018-02-10 | Authentication |  | Pending

## Stories_Requirements
Stories
Story Type | As a user/dev I want to: | Required | Dev Status | Supported by API
User | Sign in w/ a username & password | Y | Active
User | Create a username & password w/password confirmation | Y | Active
User | Change my password using current and new password | Y | Active
User | Logout of the app | Y | Active
User | Keep track of player 1 & player 2 stats | ? | Future
User | Be notified when it's my turn | ? | Future
User | Be notified when I'm waiting for my turn | ? | Future
User | Chat w/ my opponent | ? | Future
User | Select, upload, or link to an avatar | ? | Future
User | See my opponent's avatar | ? | Future
User | See my game stats (games played, won, lost, tied) | ? | Future
User | See my game history (date/time, opponent played, outcome) | ? | Future
User | See opponent's game history (games played, won, lost, tied) | ? | Future
User | Invite past opponent's to a rematch | ? | Future
User | Forfeit game if desired | ? | Future
User | See a board in my browser | Y | Active
User | See the move opponent made in a game board | Y | Active
User | Switch player turns between X and O moves | Y | Active
User | Be warned if I've made an invalid move | Y | Active
User | See outcome of the game | Y | Active
User | Play multiple games at the same time | Y | Active
User | Only see sign-in and sign-up code when not logged in | Y | Active
User | Only see the logout & change password features when signed in | Y | Active
User | Get user feedback after each AUTH action | Y | Active
Dev | Deploy to my GitHub account | Y | Active
Dev | Host the game publicly at GitHub Pages | Y | Active
Dev | Make daily commits with good comments | y | Active
Dev | Pin my GitHub repo as popular | Y | Active
Dev | Write clean concise user & project docs * README.md with completed description and website fields * Documented planning & dev process/problem solving story * Bugs/TODO/Future lists * Links to wireframes and user stories | Y | Active
Dev | Use custom game engine | Y | Active
Dev | Create a single page application (SPA) | Y | Active
Dev | Use jQuery for DOM manipulation | Y | Active
Dev | Use AJAX for API calls | Y | Active
Dev | Create new games on server | Y | Active
Dev | Update a game by storing moves | Y | Active
Dev | Visually display game stats (READ) | Y | Active
Dev | Give user feedback after each action * NEEDS CLARIFICATION. AUTH ACTIONS? CRUD? | Y | Active
Dev | Clear all forms after submit event (success/fail/status) | Y | Active
Dev |  |  | Future
Dev |  |  | Future
Dev |  |  | Future
Dev |  |  | Future
Dev |  |  | Future
Dev |  |  | Future

## Dev_Tasklist
T3 Project
Task | Main functional area | Related functional area(s)
Init board | Game engine
Start game | Game engine
Mark square when user takes a turn | Game engine
Determine outcome (win, lose, draw) | Game engine
Warn/prevent user if selecting used square | Game engine
Prompt user for action at end of game (new game, logout, ???) | Game engine
User login with result message | Authentication
User logout with result message | Authentication
user change password with result message | Authentication

## WF_T3_Wireframe_Template
Header/Logo
| Home | Rules | Sign-in | Join | About
Footer

## WF_T3_Landing_Page
Header/Logo
| Home | Rules | Sign-in/Change Password | Join | About
| Sign-in to play |  |  | Sign-in (button)
| Create an account |  |  | Create Account (button)
| How to Play |  |  | Hire the Dev
| blah | blah |  | I rock
| blah | blah |  | gimme | money
| blah | blah
| blah | blah
Footer

## WF_T3_Sign_up
Header/Logo
| Home | Rules | Sign-in/Change Password | Join | About
Enter the following to create your account
|  | Email address |  | i.e. you@me.com
|  | Choose a password |  | *************
|  | Confirm your new password |  | *************
Submit (creates account)
Results:
Sign-up success
Congrats!! You're ready to play!!!
Submit (goes to game board)
Sign-up failure (password mismatch)
I'm sorry. Your passwords didn't match. Please try again
Submit (returns to create acount modal)
Sign-up failure (account already exists)
This email is already registered.
Do you want to reset your password?
Submit (goes to reset password modal)

## WF_T3_Password_Reset
Header/Logo
| Home | Rules | Sign-in/Change Password | Join | About
Please reset your password
| Old password |  |  | *************
| New password |  |  | *************
| Confirm password |  |  | *************
Submit (resets password)
Footer

## WF_T3_Game_board
Header/Logo
| Home | Rules | Stats | Sign-out | About
Waiting for Player X to make a move
|  | X | O | X
|  | O | X | O
|  | X | O | x
| Player X: | you@me.com |  | Player O: | guest
| Games played | 100 |  | Games played | 100
| Games Won | 50 |  | Games Won | 50
| Games tied | 50 |  | Games tied | 50
| Percentage | 50% |  | Percentage | 50%
Footer